Project Implementation Schedule and Timeline

1.Overview Table

| Week | Core Focus | Features to Deliver |
| --- | --- | --- |
| 1. | Auth, Base Schema & Imports | DB schema setup with Asia/Yangon timezone; JWT Auth flow; Employee Data CSV Import; BCrypt default password generation. |
| 2. | Profiles & Course Management | Profile setup (Staff ID, Team, etc.); Target level registration (JLPT, Comm Level); Admin Course Master creation UI (Trainer, Capacity, Status). |
| 3. | Enrollment, Attendance & Progress | Course enrollment (Instant auto-approve); Attendance logger (Present/Absent/Late/Excused) with enrollment validation; Daily/Weekly study progress logging form. |
| 4. | Approver Workflow & Simple Cards | Read-only Team Viewer for Approvers; Simplified Approve/Reject actions for team study hours; Aggregate statistics calculations for Dashboards. |
| 5. | Reports, Notifications & Code Freeze | Excel Team Report export; SMTP integration (M365/Gmail) for password resets and enrollment alerts; End-to-end integration testing and bug fixing. |
| 6. | Deployment & Handover | System deployment to production servers; smoke testing; final reporting and presentation. |

2. Detailed To-Do Tasks

*yellow highlights are consider done via preparation phase but not deliverable nor validated*

Week 1: Authentication & Core Data Foundation

Goal: Establish the security layer and the ability to populate the system with users.

- Database Setup: Initialize the schema with UTF-8 support and set the timezone to Asia/Yangon.

- Auth Module: Implement JWT authentication and BCrypt password encryption.

- Employee Import: Build the utility to import Active/Inactive employee data and generate default passwords.

- Access Control: Create the Role-Based Redirect logic for Admin, Learner, and Approver dashboards.

- Security Baseline: Implement HTTPS requirements and SQL injection/XSS prevention filters.

Week 2: Profile Management & Master Data Seeding

Goal: Allow users to define their targets and Admins to set the "rules of the game."

- Profile Setup: Build the Learner UI for Staff ID, Team, and Service Year.

- Target Levels: Implement forms to register JLPT Current/Target levels and Japanese Communication levels.

- Skillset Import: Create a simplified import for technical skills based on the provided Excel structure.

- Admin Seeding: Seed the Holiday Calendar and JLPT Master Data (grammar/vocab/kanji counts) directly into the DB.

- Password Management: Finalize the Forgot Password flow and the Force Password Change on first login.

Week 3: Course Management & Attendance

Goal: Enable the educational cycle of enrollment and attendance tracking.

- Course Master: Create the Admin UI to manage Course ID, Name, Trainer, and Capacity.

- Course Status: Implement logic for Draft, Open, and Ongoing statuses.

- Learner Enrollment: Build the "Available Courses" view and the Enrollment action (set to auto-approve for Week 3).

- Attendance Module: Build the Attendance Register for Learners (Present, Absent, Late, Excused).

- Validation: Ensure unenrolled users cannot register attendance.

Week 4: Progress Tracking & Approver Workflow

Goal: Capture daily learning data and give managers visibility.

- Progress Logger: Build the Learner form for Grammar, Vocabulary, and Kanji counts plus Reading/Listening minutes.

- Study Plan: Implement the interface for setting Office and Self-study hour plans.

- Approver Dashboard: Create a read-only list for PMs/HODs to view their Team's Study Progress.

- Simplified Approval: Build the Approve/Reject buttons for study hours and progress updates.

- Status Logic: Implement the calculation for Low/Achieve/High study status (e.g., 80%–110% = Achieve).

Week 5: Dashboards, Reporting & Final Polish

Goal: Consolidate data into visual summaries and ensure the system is production-ready.

- Learner Dashboard: Display summary cards for Attendance %, Study Progress, and Upcoming Courses.

- Admin Dashboard: Implement high-level metrics: Total Employees, Active Learners, and JLPT Statistics.

- Export Engine: Build the Excel Export functionality for Team and Admin reports.

- SMTP Integration: Connect the email service for Password Resets and Enrollment Notifications.

- Code Freeze: By the end of Day 25, stop all feature development for final Bug Squashing and performance checks.